10th ACCSQ –ASEAN COSMETIC COMMITTEE MEETING

25-26 JUNE 2008, BALI, INDONESIA

BRUNEI DARUSSALAM - Country Progress Report on the Implementation of AHCRS

1. Progress Report in preparation for the implementation of ASEAN Cosmetic Directive at National Level:

i. The transposed ACD into national regulations i.e. the Medicines (Cosmetic Products) Regulations 2007 has been approved and gazetted on 31 December 2007.

ii. Guidelines for Notification of Cosmetic Products in Brunei Darussalam, Cosmetic Product Notification Form and the SOP for Handling Cosmetic Notification have been approved.

iii. Due to delay in the finalization of the SOPs and also difficulties and understanding encountered by responsible persons/companies in filling the notification forms, the Cosmetic Products Notification Procedure implementation has been delayed from 1 April 2008 to 1 June 2008. Since then, it has been successfully implemented on the 3 June 2008.

· 146 notifications received (as of 21/6/2008).

· 99 notifications acknowledged.

iv. Grace periods for notification of existing products have also been revised accordingly:

· High Risk: 1 June 2008  – 30 November 2008

· Cosmetic products for application on the region around the eye and on the lips.

· Oral dental hygiene products.

· hair dyes.

· Medium Risk: 1 December 2008 – 31 May 2009

· Leave-on cosmetic products i.e. for applications on the hair, scalp, skin, nails without rinsing.

· Low Risk: 1 June 2009 – 30 November 2009

· Rinse-off cosmetic products i.e. for application on the hair, scalp, skin or nails, which remain in traces after rinsing or use. 

2. Training

· National Training Workshop on PMS 2-3 for Cosmetic Products Regulators and Industry (jointly organized with APRIS II), 11 – 13 March 2008.

· Training on filling the Cosmetic Product Notification Form for Responsible Person / Company placing the products, April – May 2008.

